## Slide 2: DESIGN ENHANCEMENTS
DESIGN UPDATE

## Slide 3: PROJECT PHASING

## Slide 4: Phase 1 Segment 2
Design changes made pursuant to coordination with stakeholders in Houston to Commerce block
  Entertainment plaza next to Alameda Theater
    More diversity for events
    Better use of space
  Sunken Gardens
    Allows more open space in plaza at street level
    Provides more useful space at creek level

## Slide 5: Phase 1 Segment 2
Early out packages submitted to SDJV
  WP 11: Demolition and utility work
    Cost submitted: $4 million
  WP 12: Heavy Civil Houston to Dolorosa
    Cost estimate due December 12
February 2018: 90% design submittal
May 2018: 100% design submittal
July 2018: Submittal of Guaranteed Maximum Price

## Slide 8: Phase 2
Design to resume in June 2018
  Completion in fall 2018
  Start of construction late 2018 or early 2019
  Complete construction late 2020

## Slide 9: Commissioners Court
December 19th Approval Recommendations:
Segment 1.2 design changes
Additional design fees for Segment 1.2
Additional preconstruction fees
NTP with construction of early out packages

## Slide 10: DESIGN ENHANCEMENTS
CONSTRUCTION UPDATE

## Slide 11: Segment 1.1
Sundt-Davila JV on schedule to complete construction of segment 1.1 by May 5, 2018.
Coordination with design team ongoing

## Slide 12: DESIGN ENHANCEMENTS
QUESTIONS
& COMMENTS