## Slide 1
Est. May 5th 2018

## Slide 2
PROJECT PHASING

## Slide 14
PHASE 1.2 DESIGN
90% design submitted March 31
  Some design changes in Houston to Commerce block
100% design to be completed May 31
Design Charrette April 11

## Slide 19
PHASE 1.2 CONSTRUCTION
  Early Work Package 11
    Demolition of former Dollar General building complete
    Utility work on hold until after Fiesta
    Calder Alley exploratory trenches complete
  Early Work Package 12
    Demolition of Alameda walkway complete
    Drilled pier construction to start late April

## Slide 23: Phase 1.2 Timeline
100% submittal May 31
90% submittal Feb 28
Guaranteed Maximum Price July 31
Begin Full Construction Late Summer
Begin EWP Construction in February
Construction Completion Mid-2020

## Slide 24: QUESTIONS