## Slide 2: San Pedro Creek Status Update
Phases 1.1 and 1.2 Construction
Phase 1.2 Design

## Slide 3: PROJECT PHASING

## Slide 4: DESIGN ENHANCEMENTS
CONSTRUCTION UPDATE

## Slide 5: Phase 1.1 Construction Update
  Sundt-Davila JV on schedule to complete construction of Phase 1.1 by May 5, 2018
  Travis Gatehouse and wall complete
    Impoundment gate received
  Arsenal Pump Station construction ongoing
  New drone video shot February 26

## Slide 7: Phase 1.2 Construction Update
Early Work Package 11
  Former Dollar General building no longer stands
  Utility relocations ongoing
Early Work Package 12
  Demolition and heavy civil work delayed due to cultural artifacts encountered in Calder Alley
  Trenching plan to conduct additional investigations developed and approved by OHP, THC and USACE

## Slide 9: Phase 1.2 Construction Update
  Full construction to begin late summer or early fall
    Tentative construction completion projection
      Mid-2020 to Mid-2021
  Multiple layers of coordination required
    Public and Stakeholder meetings to be scheduled
  Commerce Street Project Coordination
    Project schedules must be closely coordinated
  Priority is to minimize impacts to downtown activities

## Slide 10: DESIGN ENHANCEMENTS
DESIGN UPDATE

## Slide 11: Phase 1.2 Design Update
Design team submitted 90% plans to SDJV on February 28
  SDJV will review and provide comments
100% design submittal due May 31
  Deliverable date may be impacted by requested design revisions
Design team and SDJV will continue to work together as design progresses

## Slide 12: DESIGN ENHANCEMENTS
QUESTIONS
& COMMENTS