## Slide 1
Est. May 5th 2018

## Slide 3: Phase 1.2 Construction Update
Early Work Package 11: Demolition and Utility relocation
Additional Calder Alley Archeological Mitigation
Raba Kistner developing plan for additional investigations
  Plan to be submitted to COSA OHP and THC for approval

## Slide 10: Phase 1.2 Construction Update
Early Work Package 12: Heavy Civil Construction
AH Beck mobilized to the site of the Dollar General to begin drilled piers on 4/30
Groundwater mitigation required
  Initial testing did not find contaminants above the minimum levels
  No treatment required before discharging into creek
  Continual testing will be conducted

## Slide 11: Phase 1.2 Construction Update
Commerce Street construction
Full closure to begin in June
  3-month duration
One lane open beginning early September
  13-month duration
Coordination with COSA project team ongoing
  Street project to let in September

## Slide 12: Phase 1.2 Design Update
Design team working on 100% completion
  QA/QC submittal May 31
  Final submittal June 15
Guaranteed Maximum Price submittal August 15
Coordination with SDJV ongoing

## Slide 13: Partner Coordination
Executive Committee
  David Smith, County Manager, Bexar County
  Lori Houston, Assistant City Manager, City of San Antonio
  Mike Frisbie, Director, Transportation and Capital Improvements, City of San Antonio
  Suzanne Scott, General Manager, San Antonio River Authority
May 21: Regular Monthly Meeting
April 12: City Council approved O&M Agreement

## Slide 14
QUESTIONS
& COMMENTS